## ToDo
Start | End | ToDo | Status | Open points
2025-05-13 | 2025-05-13 | Reading documentation | 100% | The APU operations seem fully automatic, the only control seems to be a 3-positions switch (off/run/start)
2025-05-13 | 2025-05-13 | Listing existing components from documentation | 100% | Document "APU_caracteristics.xlsx". If evry component is present and in good condition, the documents suggest that the APU could start
2025-05-13 | 2025-05-15 | Checking if the components are indeed on the APU | 100% | What does a RAM air door looks like ? Exept that, all components needed to run the APU seem to be there
2025-05-14 | 2025-05-16 | Finding wiring diagrams for the beam that goes in the control pannel | 100% | I sent an e-mail to people who succeded in wiring the APU (Ian F. Bennett). He doesn't have the diagrams. Ian suggested to create a new wiring harness and plug each component separately without caring of the electric beam. In the end he sent me a wiring diagram with corresponding pins for a GTCP85-98C similar to the GTCP85-98D
2025-05-14 | 2025-05-20 | APU caracteristics | 100% | Finding if the lab is suitable for APU testing. I still need to know the characteristics of the lab (air mass flow...)
2025-05-14 | 2025-05-19 | Listing components needed to build a control pannel | 100% | How much pressure sensors are needed ? There are 2 stages in the compressor. Order on the document APU_caracteristics.xlsx
2025-05-16 | 2025-05-16 | Finding where the master switch goes | 100% | The master switch is supposed to launch the automatic starting procedure of the APU.
2025-05-15 | 2025-05-22 | Designing an experimental setup | 100% | The part of the task about the starting (control panel) is finished
2025-05-22 | 2025-06-10 | Designing an experimental setup | 100% | Finding the fuel tank, fuel piping, exhaust piping
2025-05-23 |  | Designing an experimental setup | 60% | Electrical load
2028-05-28 |  | Listing missing components | 70% | To build the electrical load and the piping
2025-05-30 | 2025-06-10 | Reception of components for the control panel | 100% | Recieved : 4 relays, circuit breaker, emergency switch, fuel feed line connector. Missing : 37 pin connector
2025-05-30 |  | Building the control panel | 70% | Just need to sloder evrything according to the diagram
2025-06-17 |  | Troubleshooting the connections | 50% | The pins on the 37-pin connector don't correspont to the documentation
2025-06-23 | 2025-06-26 | Checking existing documentation | 100% | I searched in the full manual (91 chapters) but couldn't find anything useful
2025-06-23 | 2025-06-24 | Testing the pins | 100% | Testing the pins on the beam using a generator and a multimeter, drawing the corresponding electrical diagram
2025-06-26 |  | Searching for documentation | 10% | I contacted Honeywell Aerospace to ask them for the exact chapter of the manual that is missing (49-20-18), the chapter is "wiring dirgram for GTCP85-98-D APU"
|  | Disassembling the APU to check the connexions to each component | 0%
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: When they are not ar 0% or 100%, those might be random numbers

## Gantt chart
Provisional work schedule
Week |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Priority | %
Task | Deliverable
Litterature review
Study APU maintenance manuals and technical documeents | None | [17 empty] | 0
Identify key requirements for startup and basic operation | List of requirements | ok | [16 empty] | 0
Basic experimental setup design
Propose a conceptual design for placing the APU in the laboratory environnement | CAD model ? plan ? diagram ? |  | ok | [15 empty] | 0
Identify necessary peripheral devices (fuel system, oil system...) | List of peripheral devices with location and installation procedure on the APU |  | ok | [15 empty] | 0
Define basic safety requirements for testing | List of safety requirements |  | ok | [15 empty] | 0
Peripheral devices installation | Making sure evry device is available at LiCEM. If not, make an order. Installation of each device and checking the proper working |  |  |  | ? | [13 empty] | 0
Simplified electronic control system plan
Outline key components needed for startup control (switches, relays, sensors) and obtain official prices quotes from suppliers for their purchase. Potential integration with national instruments hardware | List of key components with price and availability. Location and diagram for installation on the APU. List of steps for the starting procedure, including the peripheral devices |  | ok | [15 empty] | 0
Installation of control components | Making sure evry device is available at LiCEM. If not, make an order. Installation of each device and checking the proper working | [5 empty] | ? | [11 empty] | 0
Testing | Testing if evry component can work at the same time. I might have to place the APU in the laboratory environnement to see if a startup is possible. Test of the APU with Ziga | [5 empty] | ? | [11 empty] | 0
Basic measurement system selection
Identify essetial parameters to measure (temperature, pressure) | List of parameters | [17 empty] | 0
Select suitable sensors and consider integration with national instruments hardware. If sensors are not available in the laboratory, obtain official price for their purchase | List of sensors with price and location, installation procedure on the APU | [17 empty] | 0
Simple LabView interface draft (optionnal)
Create a basic interface in LabView for monitoring (not full automation) | [18 empty] | 0
Set up basic data acquisition (if possible, with simulated inputs) | [18 empty] | 0
Final documentation and presentation
Summarize findings, system design and recommendations for future work | [18 empty] | 0
Deliver a final report and presentation on the project | [18 empty] | 0
End of week (friday) |  | 2025-05-16 | 2025-05-23 | 2025-05-30 | 2025-06-06 | 2025-06-13 | 2025-06-23 | 2025-06-30 | 2025-07-04 | 2025-07-11 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29